## Sheet1
WESTERN WASHINGTON PHASE II MUNICIPAL STORMWATER PERMIT IMPLEMENTATION SCHEDULE
[5 empty] | 2013 |  |  |  |  | 2014 | [11 empty] | 2024 | [6 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
|  |  | TASKS | DEPT / DIV | August 1st | September | October | November | December 1 | January | February 16 | March 31 | April | May | June | July | August 15 | September | October | November | December | January 1 | July | August | September | October | November | December 1st | January 1st | February 1st | March 31 | April | May 31 | June | July 1 | August 15th | September | October 1st | November | December 31 | January 1st | February 1 | March 31 | April 1st | May 31 | June | July 1st | August 15th | September 1st | October | November | December 31st | January | February 1st | March 31 | April | May 31st | June 30th | July 1st | August 15th | September | October | November | 2024-12-31 | January 1st | February 2 | March 31 | April | May 31st | June | July | August 15th | September | October | November | December | January 1st | February 1 | March 31 | April 1st | May 31 | June | July 31
S5 | Stormwater Management Plan (SWMP)
| A1 |  | SWMP Develop & Implement
| A2 |  | SWMP Plan Annually Updated
| A3 | a. | Track Costs or Estimated Costs (Include in Annual Report)
|  | b. | Track Inspections, Enforcements & Public Educ. Activities
| A4 |  | Continue Implementation of Existing Programs
| A5 | a. | Include Coord. Mech. with Other Entities (If Applicable)
|  | b. | SWMP Includes Internal Coord. Mechanisms, add to Annual Report
| C1 | Stormwater Planning
|  | a. | Convene an Interdisciplinary Team for the Program
|  | b. | Coordination with Long-range Plan Updates (Include in Annual Report)
|  | c.i. | Continue to require LID Principles/BMPs with code/standard updates
|  | c.i.a. | Assess/evaluate barriers to LID implementation in report
|  | d. | Stormwater Management Action Planning (SMAP)
| C2 | Public Education and Outreach Program (Individually or Group)
|  | a.i. | E&O for 1 target audience and 1 subject area
|  | a.ii. | Behavior change: 1 target audience and 1 BMP
|  | a.ii.b. | Evaluate the Effectiveness of Ongoing Behavior Change
|  | a.ii.c. | Develop a Community-Based Social Marketing Strategy
|  | a.ii.d. | Implement a Community-Based Social Marketing Strategy
|  | a.ii.e. | Evaluate and Report on Behavior Change
|  | a.iii. | Create and Advertise Stewardship Opportunities
| C3 | Public Involvement and Participation
|  | a. | Involve Public in SWMP Development and Implementation
|  | a.i. | Annually Document specific public involvement opportunities
|  | a.ii. | Document methods used to identify overburdened communities
|  | b. | SWMP & Annual Report Website Posting
| C4 | MS4 Mapping and Documentation
|  | a. | Ongoing Stormwater Mapping - Periodically update
|  | b.i. | Map Size and Material Type for Known MS4 Outfalls
|  | b.ii. | Map and assess acreage owned by permittee for treatment and flow control
|  | b.iii. | Map permittee-owned properties with tree canopy based on existing data
| C5 | Illicit Discharge Detection & Elimination (IDDE) Program
|  | a. | Include Reporting and Correcting/Removing IC/IDs
|  | b. | Inform Public Employees, Businesses, General Public about IDDE
|  | c. | IDDE Ordinance Update/Evaluate
|  | c.ii.e | Routine external building washdown without detergents
|  | d. | IDDE Procedures
|  | d.i.a. | Field Screen 12% of MS4 Annually
|  | d.i. | Document Field Screening Methodology
|  | d.ii. | Publicly List Phone #'s for Reporting Spills
|  | d.iii. | Ongoing Training all Muni. Field Staff
|  | e. | IDDE Program
|  | g. | Report Spills Found, Reported, or Investigated using WQWebIDDE
| C6 | Controlling Runoff from New Development, Redevelopment, and Construction Sites
|  | a. | Update/Evaluate Construction Site Runoff Ordinance
|  | b.i. | Include Appendix 10
|  | b.ii. | Adopt Variance Criteria Equiv. to Appendix 1
|  | b.iii. | Ord./ Reg. Mech. Giving Legal Authority to Inspect
|  | c.i. | Review All Stormwater Site Plans
|  | c.ii. | Pre-Con Site Inspection
|  | c.iii. | Inspect All Sites for Erosion and Sediment Controls
|  | c.iii. | Enforce ESC as Necessary
|  | c.iv. | Final ESC Inspection
|  | c.iv. | Maintenance Plan for New Facilities (Bond Program)
|  | c.iv. | Enforce Maintenance Plan (Bond Program)
|  | c.v. | Minimum 80% Compliance with Inspect. Requirements
|  | c.vi. | Enforcement Strategy for Non-compliance
|  | d. | NOI Avail. Electronically (ISGP, CSGP), Enforce All Sites
|  | e. | Staff Training (Permitting, Plan Review, Inspections, Enforcement)
|  | e. | Document Staff Training
| C7 | Stormwater Management for Existing Development
|  | a. | Implement a program to control or reduce stormwater discharge to waters of the state from existing development
|  | a.i | Strategic Stormwater Investments in SMAP
|  | a.ii | Opportunistic stormwater investments outside of SMAP areas
|  | b. | Fund, construct, implement, projects that meet assigned equivalent acreage (submit in Annual Report)
|  | c.iv | Each permittee is required to manage at least 0.3 acres within their own jurisdiction, may receive credit for contributing to a regional goal
|  | d | Report the amount of estimated or projected equivalent acres managed by stormwater facility retrofits and SMAP project costs for the 2029 permit term.
| C8 | Source Control Program for Existing Development
|  | a. | Implement a Program to Prevent/Reduce Pollutants using applicable BMPs and enforceable ordinances/documents
|  | b.i. | Establish an Inventory of Public/Private Properties based on Appendix 8
|  | b.ii. | Establish an Inventory of other pollution generating sources: Home-Based Businesses and Mutli-family sites
|  | c.i | Implement Source Control Inspection Program: Education Materials to all identfied sites with a buisness addresses
|  | c.ii | Annually Inspect 20% of Businesses/Properties on Source Control List
|  | c.iii. | Inspect 100% of Sites Identified through Complaints
|  | c.iv. | Permittees may count inspections based on complaints and sites where the property owner denies entry to the 20% inspection rate
|  | c.v. | Annual reporting of inspections organized by buisness type or activiites with the potential to generate pollutants to the MS4
|  | d.i | Implement a Progressive Enforcement Policy: Follow up with sites that failed inspection
|  | d.ii | Implement a Progressive Enforcement Policy: Take enforcement action on sites that fail follow up inspections
|  | d.iii. | Implement a Progressive Enforcement Policy: Maintain Records, document site visits, inspection records, notices of violations etc.
|  | d.iv. | Permittees may refer non emergeny violations of local ordinances to Ecology provided there is a documented progressive enforcment.
|  | d.v. | Permitees in compliance with the terms of this permit will not be held liable by Ecology for receiving water impacts caused by industries or other permitees covered by an NPDES permit issued by Ecology.
|  | e. | Staff Training for Source Control Program
| C9 | Operations and Maintenance
|  | a. | Maintenance Standards Equivalent to SMMWW & Update
|  | a. | Develop Standards for Facilities without Maintenance Standards
|  | a.ii | Perform Timely Maintenance (Public Facilities and CBs)
|  | b.i.a. | Implement Ordinance for Responsible Party, Requires Inspections, Establishes Enforcement
|  | b.i.b. | Annual Inspections of Treatment/Flow Control Facilities/BMPs that Discharge to MS4 (pursuant to 2007-2024 permit)
|  | b.i.c. | Inspect All Permanent Treatment/Flow Control Facilities/BMPs every 6 months in new SFR until 90% of lots are built out. Enforce as Needed.
|  | b.ii. | Compliance with b.i.b. and c. = Achieving 80% of Inspections
|  | b.iii. | Require property owners to provide annual certification by a qualified thrid party, in lieu of requiring continued access for Permittee staff
|  | b.iv. | Keep Records of Inspections, Maintenance, Enforcement
|  | c.i. | Annual Inspections of Publicly Owned/Operated Treatment/Flow Control Facilities/BMPs
|  | c.ii. | Spot Checks of Facilities/BMPs after 10-year, 24-hour Storm Event +
|  | c.iii. | Inspect all Catch Basins and Inlets Every 2 Years
|  | c.iv. | Compliance = Established Inspection Program and 95% of Inspections
|  | d. | Document all Practices, Policies, Procedures to Reduce Runoff from City Lands and Roads
|  | e. | Develop and implement a municipal street sweeping program
|  | e.i. | Apply street sweeping to publically owned roads in MS4 drainage areas that discharge to outfalls focusing on high priority areas
|  | e.ii. | Street sweep at least once between July and September each year and two additional times a year as determined by the permittee (one sweeping event is required in 2027)
|  | f | Implement SWPPP (ongoing), Describe BMPs, Annual Inspections
|  | f.i-f.iii. | Update SWPPP (ongoing), Describe BMPs, Annual Inspections
|  | g. | Ongoing Training all Staff: WQ, Inspections, Maintenance Standards, SWPPPs, BMP selection. Maintain Training Records.
|  | h | Maintain Inspection and Maintenance Records
S8 | Monitoring & Assessment
| A1 |  | Pay into Collective Fund to Implement Regional Small Streams and Marine Nearshore Monitoring (one-time cost)
| A2 |  | Notify Ecology in Writing about Status and Trends Monitoring Option
|  | a. | Pay into Collective Fund to Implement Regional Receiving Waters Status and Trends Monitoring
| B1 |  | SWMP Effectiveness & Source Identifation Studies - Collective Fund (one-time cost) | [6 empty] | Notification to DOE | [7 empty] | Annual Payments Start
| B2 |  | Notify Ecology in Writing about Option Effectiveness & Source Identifation Studies
|  | a. | Pay into Collective Fund to Implement SAM Studies
| B3 |  | Submit Records of SWMP Activities to SAM Coordinator upon Request (within 90 days)
| C1 |  | Stormwater discharge modeling is an alternate option to A2 and B2
|  | a. | Monitor 3 independent discharge locations (6 locations necessary if using alternate option for both A2 and B2
|  | b. | Submit an ecology draft stormwater discharge monitoring AQPP for review and approval
|  | c. | Flow monitoring shall begin, fully implemented by Oct/2026
|  | d. | Data Reported Annually
|  | d.ii | Publish Final Report
| D1 |  | Section applies to option A1 and B1
| D2 |  | Permittee payment amounts are listed in appendix 11
S9
| A1 |  | Annual Compliance Report
G18
Apply for permit renewal
|  |  | LEGEND: |  |  |  | Effective & Expiration Dates of Permit | [17 empty] | Ongoing Requirement | [15 empty] | New Requirement | [12 empty] | Permit Deadline