## 2024-2029 Draft
[6 empty] | Prep Work | [6 empty] | Permit Deadline | [8 empty] | Ongoing Requirement | [11 empty] | Requirement Completed | [11 empty] | Effective/Expiration Dates of Permit
CHAPTER | SECTION | SUB-SECTION |  | WESTERN WASHINGTON PHASE II MUNICIPAL STORMWATER PERMIT IMPLEMENTATION SCHEDULE - Algona
[5 empty] | 2024 |  |  |  |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
|  |  | SWMP REFERENCE | TASKS | August 1 | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August 1
| C1 |  |  | Stormwater Program Coordination
| A1 |  | SP-C-1 | Hold monthly internal status meetings on NPDES permit compliance.
| A2 |  | SP-C-2 | SWMP Plan Annually Updated
| A2 |  | SP-C-3 | List of internal coordination mechanisms describing how departments are inter-related | [19 empty] | 31
| A2 |  | SP-C-4 | Attend NPDES Permit Coordinators Forum Meetings
| A2 |  | SP-C-5 | Attend STORM meetings
| A3 | a. | SP-C-6 | Track Costs or Estimated Costs
|  | b. | SP-C-7 | Track Inspections, Enforcements & Public Educ. Activities
| A5 | a. | SP-C-8 | Include Coord. Mech. with Other Entities (If Applicable)
| C1 |  |  | Stormwater Planning
Coordination with Long-Range Plan Updates
|  | a. | SP-C-1 | Form Interdisiplinary Team
|  | b. | SP-C-2 | Describe how stormwater management needs and protection/improvement of receiving water health are (or are not) informing the long-range or comprehensive planning update processes and influencing policies and implementation strategies. Report shall describe the water quality/watershed protection policies/strategies/codes/other measures intended to protect and improve local receiving water health through planning, considering stormwater management needs or limitations | [31 empty] | 31
|  | c. |  | LID Code-Related Requirements
|  | c.i | SP-LID-1 | Continue to require LID
|  | c.i.(a) | SP-LID-2 | In a report, assess/document newly identified administrative or regulatory barriers to implementing LID (since 2013); List measures developed to address the barriers; Describe mechanisms adopted to encourage LID (if applicable) | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | c.i.(a) | SP-LID-3 | Adopt and implement tree canopy goals and policies to support stormwater management and water quality improvement in receiving waters. | [52 empty] | 31 |  |  | 31
|  | d. |  | Stormwater Management Action Planning (SMAP)
|  | d.i | SP-SMAP-1 | Complete a SMAP for at least one new high priority catchment area or additional actions for an existing SMAP. Provide 1) description of stormwater facility retrofits needed, 2) land management strategies, 3) targeted stormwater management actions including IDDE field screening, prioritization of source control inspections, O&M inspections, education/outreach behavior change programs 4) If needed ID changes to long-range plans to address SMAP priorities 5) Implementation schedule (6 yrs, 20 yrs), 6) schedule to provide future assessment | [28 empty] | 31
| C2 |  |  | Public Education and Outreach
|  | a.i.(c) | EDUC-1 | Select one priority audience and one subject area for education: For the general public, provide education on general impacts of stormwater on City’s website (document) | [5 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | a.i | EDUC-2 | Promote proper pet waste management behavior with pet waste stations at parks (document)
|  | a.iii | EDUC-3 | Provide stewardship opportunities on City’s website (Conservation District Events, other storm related community events); Document opportunities advertised.
|  | a.ii | EDUC-4 | Select one priority audience and one BMP to focus on for behavior change.
|  | a.ii | EDUC-5 | Report on effectiveness of current ongoing behavior change campaign including lessons learned and recommended changes (can forgo this if creating a new campaign) | [11 empty] | 1
|  | a.ii | EDUC-6 | Develop social marketing practices and methods and develop a campaign tailored to the community. This will include a program evaluation plan that either 1) develops a more effective implementation of the existing campaign 2) expands existing campaign or 3) develop strategy/schedule for new audience/BMP. | [23 empty] | 1
|  | a.ii | EDUC-7 | Implement behavior change campaign | [25 empty] | 1
|  | a.ii | EDUC-8 | Report on changes in understanding/adoption of targeted behavior and recommended changes to campaign to be more effective | [55 empty] | 31
| C3 |  |  | Public Involvement and Participation
|  | b. | PI-1 | Document methods used to identify overburdened communities | [28 empty] | 31 | [26 empty] | 31
|  | b. | PI-2 | Hold public meeting on the Annual SWMP via the City Council; Document public involvement opportunities for overburdened communities to participate in the decision-making processes of the SWMP.
|  | b. | PI-3 | Hold public meeting on the Update of the SMAP; Document public involvement opportunities for overburdened communities to participate in the decision-making processes of the SWMP. | [55 empty] | 31
|  | b. | PI-4 | Post final SWMP and Annual Report to City Website | [8 empty] | 30 | 31 | [10 empty] | 30 | 31 | [10 empty] | 30 | 31 | [10 empty] | 30 | 31 | [10 empty] | 30 | 31
|  | a. | PI-5 | Post public opportunities to get involved on City website (i.e. links to Sound Salmon Solutions, King County Conservation District, Medina County, Dept. of Ecology, etc.); Document opportunities advertised and provide with Annual Report.
| C4 |  |  | MS4 Mapping and Documentation
|  | a. | MAP-1 | Maintain existing map of: MS4 outfalls, known MS4 discharge points, receiving waters, SW treatment and flow control BMPs/facilities owned by the City, areas that do not discharge SW to surface waters, tributary conveyance to all knows outfalls/discharge points with a 24" nominal diameter or larger (incl. type, material, size, drainage area, and land use), Connections to MS4 after Feb 16, 2007, all connections authorized to the MS4, known connections from MS4 to privately owned SW system.
|  | b.i | MAP-2 | Submit locations of all known MS4 outfalls according to the standard templates and format provided in the annual report. This will include the size and material of the outfall. | [19 empty] | 31
|  | b.ii | MAP-3 | Develop methodology to map and asses acreage of MS4 tributary basins to outfalls or discharge points that have stormwater treatment and flow control BMPs/facilities owned by the City. Submit map and breakdown of acres managed or unmanaged by treatment and flow control facilities. | [5 empty] | 1 | [34 empty] | 31
|  | b.ii | MAP-4 | Begin mapping jurisdiction-owned or operated properties with tree canopy based on available data. | [5 empty] | 1 | [46 empty] | 31
| C5 |  |  | Illicit Discharge Detection & Elimination Program
|  | a., e. | IDDE-1 | Maintain IDDE program for reporting, correcting and/or removing illicit connections or spills. Document issues identified through field screening, inspections, complaints/reports, construction inspections, maintenance inspections, source control inspections and/or monitoring. Maintain documented procedures for addressing illicit discharges/connections.
|  |  | IDDE-2 | For spills:
|  | G3 |  | · Immediately respond to all illicit discharges which are determined to constitute a threat to human health, welfare or the environment (see General Condition G3).
|  | S4.F.1 |  | · Investigate (or refer to appropriate agency) within 7 days, on avg., any complaints/reports/monitoring that indicate a potential illicit discharge.
|  | g. |  | · Investigate within 21 days of any report/discovery of a suspected illicit connection to determine the source, nature and volume of discharge through the connection and party responsible.
|  | g. |  | · Upon confirmation of an illicit connection, use compliance strategy in a documented effort to eliminate illicit connection within 6 months. All known illicit connections to the MS4 shall be eliminated.
|  | g. |  | · Per Section G3, provide notice to Ecology and other spill response authorities within 24 hours of knowledge of a discharge/spill that is a threat to human health, welfare or the environment.
|  | g. |  | · Document any spill/discharge or illicit connection to Ecology’s online WQWebIDDE.
|  | b. | IDDE-3 | Provide general public with information related to IDDE including hotline on City website. List actions in Annual Report. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | c. | IDDE-4 | Implement/Review ordinance to prohibit illicit discharges including escalating enforcement actions. | [36 empty] | 31
|  | d. | IDDE-5 | Continue to use the Illicit Connection and Illicit Discharge Field Screening and Source Tracing Guidance Manual for field screening. Cite this source in Annual Report. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | d.i.(a) | IDDE-6 | Field Screen average of 12% of system for IDDE each year (Maintain records of which areas have been field screened and date inspected). This is typically done through cb inspections.
|  | d.ii | IDDE-7 | Maintain hotline for reporting spills/illicit discharges; Document all calls and within the Annual Report, note how the hotline was advertised. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | d.iii | IDDE-8 | Renew IDDE training for field staff and public employees (Track each training session with names of employees, their positions and date)
|  | f. | IDDE-9 | Include WQWebIDDE report with Annual Report | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
| C6 |  |  | Controlling Runoff from New Development, Redevelopment and Construction Sites
|  | a. | CTRL-1 | Implement ordinance that addresses runoff from new development, redevelopment and construction site projects including the adoption of Appendix 1 of the Permit (which includes adoption of the Stormwater Management Manual for Western Washington) and allows to inspect/enforce maintenance standards for private stormwater facilities;; Cite code reference in Annual Report | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 |  |  | 30 | [8 empty] | 31 | [11 empty] | 31
|  | c.i | CTRL-2 | Review site plans for compliance with City Code (Keep track of number of site plans reviewed)
|  | c.ii, c.iii | CTRL-3 | Inspect constructions sites prior to and during construction for erosion control (Maintain inspection records; see CTRL-6).
|  | c.ii, c.iii | CTRL-4 | Inspect all stormwater treatment and flow control BMPs/facilities, and catch basins, in new residential developments every six months, until 90% of the lots are constructed
|  | v. | CTRL-5 | Provide post construction inspections prior to approval for compliance with City Code and to verify a maintenance plan is in place. (Maintain inspection records; see CTRL-6).
|  | vi. | CTRL-6 | Maintain records of inspections (Include name of inspector, date, findings, warning letters, notices of violations, enforcement actions).
|  | d. | CTRL-7 | Make available (via website and developer checklist) the electronic links to Ecology’s Construction Stormwater General Permit Notice of Intent and the Industrial Stormwater General Permit Notice of Intent and a link to the online registration requirements for UIC wells to developers.
|  | e. | CTRL-8 | Train staff in the site plan review process, inspections, and enforcement. Maintain records of this training and names of staff trained.
| C3 |  |  | Stormwater Management for Existing Development
|  | b. | SWM-1 | Implement stormwater facility retrofits or tailored SWMP actions (meeting criteria in Appx 12), using 1) stormwater investments ID'd in SMAP or similar stormwater planning process and/or 2) opportunistic stormwater investments outside of SMAP to improve stormwater management and infrastructure.
|  | b. | SWM-2 | Fund, start construction or completely implement project meeting assigned equivalent acreage; document in Annual Report. | [43 empty] | 31
|  | b. | SWM-3 | Develop a method and report amount of estimated or projected equivalent acres managed by stormwater facility retrofits and SMAP project costs for the 2029 permit term | [43 empty] | 31 | [11 empty] | 31
| C8 |  |  | Source Control Program for Existing Development
|  | b.i | BUS-1 | Enforce ordinance requiring source control BMPs (i.e. BMPs from the Ecology Stormwater Manual) for pollutant generating sources for existing land uses. Cite ordinance in Annual Report. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | b.ii | BUS-2 | Create inventory of public/private institutional, commercial and industrial sites that have the potential to generate pollutants and any complaint-based sources (home-based businesses, multi-family sites). Update inventory every five years | [47 empty] | 31
|  | b.iii | BUS-3 | Implement business source control inspection program including education (via mail/phone/in-person) about source control BMPs. Document all inspections (including follow-ups) with business category, number of times inspected and if enforcement actions were taken in a single list. Include this list with the Annual Report organized by business type or by activities w/ potential to generate pollutants to MS4. Also, document records of sites where the owner denies entry. |  |  |  |  | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | 1 | [17 empty] | 31
|  | b.iii(c) | BUS-4 | Inspect all complaint-based businesses for pollution generating sources and installed BMPs
|  | iv. | BUS-5 | Implement progressive enforcement policy requiring business sites to comply with stormwater requirements within a reasonable time period
|  | v. | BUS-6 | Train staff on conducting business source control inspections including inspection protocols, lessons learned, and enforcement procedures.
| C7 |  |  | Operations and Maintenance (for Municipally Owned or Operated)
|  | AR | O&M-1 | Review/Update Maintenance standards (specified in Ecology’s Stormwater Management Manual for Western Washington) | [34 empty] | 30
|  | b.i.(a) | O&M-2 /CTRL-2 | Maintain ordinance identifying responsible party for maintaining private flow control and water quality facilities and that allows inspection and enforcement of maintenance standards of these facilities | [34 empty] | 30
|  | c. | O&M-3 /CTRL-2 | Provide annual inspections of all public stormwater treatment and flow control BMPs/facilities.
-Maintain inspection records; see O&M-1.
-Document if a reduced inspection frequency is used.
-If inspection reveals that a maintenance standard is not being maintained, need to perform maintenance:
o within 1 year (all facilities except public catch basins)
o within 6 months (public catch basins) or
o within 2 years (maintenance that requires capital construction of less than $25,000).
|  |  |  | -Document when/if maintenance standard could not be met on time and attach to Annual Report. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | b.i.(b) | O&M-4 /CTRL-2 | Provide annual inspections of all private stormwater treatment and flow control BMPs/facilities. Document results/enforcements and provide follow-up inspections as needed. Any maintenance activity shall be recorded. |  |  |  |  | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | AR | O&M-5 | Maintain records of inspections and maintenance activities. List number of stormwater treatment and flow control facilities that 1) are located in the City, 2) were inspected and 3) were maintained in Annual Report. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | c.ii | O&M-6 | Spot check treatment and flow control facilities/BMPs and repair if necessary.
|  | c.iii | O&M-7 | Inspect catch basins and inlets ever 2 years; Document total number of cbs, how many inspected and how many cleaned with the Annual Report. | [16 empty] | 31 | [23 empty] | 31 | [7 empty] | 1
|  | d. | O&M-8 | Implement/document procedures to reduce stormwater impacts from all lands owned/maintained by the City and road maintenance activitiesincluding adding provisions for cleaning/maintaining building exteriors and preparing buildings for renovation/demolition. Cite documentation in Annual Report. | [7 empty] | 31 | [12 empty] | 31 | [10 empty] | 31 | [8 empty] | 31 |  |  | 31 | [11 empty] | 31
|  | e. | O&M-9 | Implement a municipal street sweeping program to target high priority areas that discharge to outfalls (high traffic roads, accessible curbed streets, areas w/ significant tire wear (roundabouts/intersections/parking lots), heavy tree canopy, commercial/industrial areas, areas that discharge to salmonids). | [35 empty] | 1
|  | d. | O&M-10 | Document road type and level of traffic served (AADT or estimated # of vehicles) of roads swept, frequency, type of sweeper, lane miles, a map of the areas and land uses swept and approximation of street waste removed. | [55 empty] | 31
|  | d. | O&M-11 | Implement SWPPP for Public Works’ Yard and any heavy equipment maintenance/storage yards. SWPPP to include annual inspections of facility to evaluate effectiveness of BMPs, ID maintenance needs which shall be documented in an inspection report or checklist.
|  | e. | O&M-12 | Train staff in O&M operations, inspection procedures, reporting water quality concerns, SWPPPs, street sweeper operation, and on efforts to reduce pollutants to runoff. Maintain records of this training, names/positions of staff trained, dates training was held, and activities or course descriptions.
S8 |  |  |  | Monitoring & Assessment
|  |  | MON-1 | Opt into Regional Stormwater Management Program | [16 empty] | 1 | [11 empty] | 1 | [11 empty] | 1 | [11 empty] | 1
Reporting
S9
| A-D |  | REP-1 | Annual Report | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31
|  | S3B | REP-2 | Attach letters notifying Ecology of relying on another entity to satisfy one or more permit obligations. | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31